## Sheet1
Sprint Retrospective
What went well ? | What went bad ? | What could be better ?
Each and every team member was given a chance to express his/ her point of view and idea | Due to some last moment complex requirement changes, few deadlines weren't met | More efficient planning of way of execution of tasks could be done
The quality of code and well-formed logic lead to very few bugs at the time of testing | Work division among team members was not balanced | Overall communication with the customer could be done with more clarity and understanding